## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-001 | As a user, I want to register and log in so that I can securely access my projects. | MUST HAVE | None | Pankaj | 3- Completed
Sprint 1 | Sprint 1 | US-002 | As a user, I want to create a project so that I can organize project documents and analysis. | MUST HAVE | US-001 | Pankaj | 3- Completed
Sprint 1 | Sprint 1 | US-003 | As a user, I want to switch between dark light and dim themes so that I can use the application according to my preference. | COULD HAVE | None | Umang | 3- Completed
Sprint 1 | Sprint 1 | US-004 | As a user, I want to upload project documents so that the system can analyze project information. | MUST HAVE | US-002 | Pankaj | 3- Completed
Sprint 1 | Sprint 1 | US-005 | As a user I want to upload document by drag and drop so that I can upload document in bulk. | COULD HAVE | US-004 | Pankaj | 3- Completed
Sprint 1 | Sprint 1 | US-006 | As a user, I want to view uploaded documents so that I can verify their contents. | COULD HAVE | US-004 | Pankaj | 3- Completed
Sprint 1 | Sprint 1 | US-007 | As a user, I want to Analyze uploaded document with AI that help me to find missing things in document and provide a good plan. | MUST HAVE | US-004 | Pankaj | 3- Completed
Sprint 1 | Sprint 1 | US-008 | As a user, I want to view the project health score so that I can understand the overall condition of the project. | MUST HAVE | US-007 | Pankaj | 3- Completed
Sprint 1 | Sprint 1 | US-009 | As a user, I want to view an analysis report so that I can understand the findings from my project documents. | MUST HAVE | US-007 | Pankaj | 3- Completed
Sprint 1 | Sprint 1 | US-010 | As a user, I want to view project risks with essential information so that I can understand the risks identified in my project documents. | MUST HAVE | US-007 | Pankaj | 3- Completed
Sprint 1 | Sprint 1 | US-011 | As a user, I want to identify missing project documents so that I can understand what documentation is still required. | MUST HAVE | US-007 | Pankaj | 3- Completed
Sprint 1 | Sprint 1 | US-012 | As a user, I want to view and export generated document so that I can share with team and save artifact. | SHOULD HAVE | US-007 | Pankaj | 3- Completed
Sprint 1 | Sprint 1 | US-013 | As a user, I want to view a project dashboard so that I can get an overview of my project. | MUST HAVE | US-002 | Pankaj | 3- Completed
Sprint 1 | Sprint 1 | US-014 | As a user, I want to chat with an AI assistant so that I can retrieve project information using natural language. | MUST HAVE | US-007 | Pankaj | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 99.5 | 5.5 | 5.8 | 4 | 6.5 | 10.5 | 6 | 6 | 7 | 5 | 6.5 | 6 | 11.5 | 7.5 | 8.5
SPRINT 1 BACKLOG
US-001 | T-001-01 | Implement user registration functionality | 2026-08-26 | 2026-08-26 | Pankaj | Coding | 3- Completed | 1 | Day 1: 0.8
US-001 | T-001-01 | Implement user registration functionality | 2026-08-26 | 2026-08-26 | Pankaj | Coding | 3- Completed | 1 | Day 1: 0.5
US-001 | T-001-02 | Implement user login functionality | 2026-08-26 | 2026-08-26 | Pankaj | Coding | 3- Completed | 1 | Day 1: 0.5
US-001 | T-001-03 | Implement user logout functionality | 2026-08-26 | 2026-08-26 | Pankaj | Coding | 3- Completed | 1 | Day 1: 0.3
US-001 | T-001-04 | Implement password hashing and validation | 2026-08-26 | 2026-08-26 | Pankaj | Coding | 3- Completed | 1 | bar: Day 1
US-001 | T-001-05 | Implement JWT access-token authentication | 2026-08-26 | 2026-08-26 | Pankaj | Coding | 3- Completed | 1 | Day 1: 0.4
US-001 | T-001-06 | Test implemented authentication flow | 2026-08-26 | 2026-08-26 | Pankaj | Unit Test | 3- Completed | 2 | Day 1: 2
US-002 | T-002-01 | Implement project create functionality | 2026-08-27 | 2026-08-27 | Pankaj | Coding | 3- Completed | 1 | Day 2: 0.5
US-002 | T-002-02 | Configure database environment for project creation functionality | 2026-08-27 | 2026-08-27 | Pankaj | Coding | 3- Completed | 1 | bar: Day 2
US-002 | T-002-03 | Implement object storage for raw document file storage | 2026-08-27 | 2026-08-27 | Pankaj | Coding | 3- Completed | 1 | Day 2: 0.8
US-002 | T-002-04 | Implement project model and schema validation | 2026-08-27 | 2026-08-27 | Pankaj | Coding | 3- Completed | 1 | bar: Day 2
US-002 | T-002-05 | Implement project creation UI | 2026-08-27 | 2026-08-27 | Pankaj | UI Development | 3- Completed | 1.5 | Day 2: 1.5
US-002 | T-002-06 | Test project creation flow | 2026-08-27 | 2026-08-27 | Pankaj | Integration Test | 3- Completed | 1 | bar: Day 2
US-003 | T-003-01 | Set up theme provider | 2026-08-28 | 2026-08-28 | Pankaj | UI Development | 3- Completed | 1 | bar: Day 3
US-003 | T-003-02 | Implement dark, light and dim themes | 2026-08-28 | 2026-08-28 | Umang | UI Development | 3- Completed | 1.5 | Day 3: 1.5
US-003 | T-003-03 | Implement theme toggle and persistence | 2026-08-28 | 2026-08-28 | Umang | UI Development | 3- Completed | 1 | bar: Day 3
US-003 | T-003-04 | Test theme switching | 2026-08-28 | 2026-08-28 | Umang | Unit Test | 3- Completed | 0.5 | Day 3: 0.5
US-004 | T-004-01 | Implement document upload API | 2026-08-29 | 2026-08-29 | Pankaj | Coding | 3- Completed | 2 | Day 4: 2
US-004 | T-004-02 | Implement file validation | 2026-08-29 | 2026-08-29 | Pankaj | Coding | 3- Completed | 2 | Day 4: 2
US-004 | T-004-03 | Implement raw file storage in object storage | 2026-08-29 | 2026-08-29 | Pankaj | Coding | 3- Completed | 1.5 | Day 4: 1.5
US-004 | T-004-04 | Create document record and persistence | 2026-08-29 | 2026-08-29 | Pankaj | Coding | 3- Completed | 1 | bar: Day 4
US-004 | T-004-05 | Implement document upload UI | 2026-08-30 | 2026-08-30 | Pankaj | UI Development | 3- Completed | 2 | Day 5: 2
US-004 | T-004-06 | Test document upload flow | 2026-08-30 | 2026-08-30 | Pankaj | Integration Test | 3- Completed | 1.5 | Day 5: 1.5
US-013 | T-013-01 | Implement project dashboard layout | 2026-08-30 | 2026-08-30 | Pankaj | UI Development | 3- Completed | 2 | Day 5: 2
US-013 | T-013-02 | Implement project overview data integration | 2026-08-30 | 2026-08-30 | Pankaj | Coding | 3- Completed | 2 | Day 5: 2
US-013 | T-013-03 | Implement project summary cards and status display | 2026-08-30 | 2026-08-30 | Pankaj | UI Development | 3- Completed | 2 | Day 5: 2
US-013 | T-013-04 | Test project dashboard | 2026-08-30 | 2026-08-30 | Pankaj | Unit Test | 3- Completed | 1 | bar: Day 5
US-005 | T-005-01 | Implement drag-and-drop document upload UI | 2026-08-31 | 2026-08-31 | Umang | UI Development | 3- Completed | 1.5 | Day 6: 1.5
US-005 | T-005-02 | Implement multiple-file selection handling | 2026-08-31 | 2026-08-31 | Umang | Coding | 3- Completed | 1.5 | Day 6: 1.5
US-005 | T-005-03 | Connect bulk upload to document upload API | 2026-08-31 | 2026-08-31 | Pankaj | Coding | 3- Completed | 2 | Day 6: 2
US-005 | T-005-04 | Test bulk document upload | 2026-08-31 | 2026-08-31 | Pankaj | Integration Test | 3- Completed | 1 | bar: Day 6
US-006 | T-006-01 | Implement uploaded document listing | 2026-09-01 | 2026-09-01 | Pankaj | Coding | 3- Completed | 1.5 | Day 7: 1.5
US-006 | T-006-02 | Implement document metadata retrieval | 2026-09-01 | 2026-09-01 | Pankaj | Coding | 3- Completed | 1 | bar: Day 7
US-006 | T-006-03 | Implement document preview and viewer UI | 2026-09-01 | 2026-09-01 | Pankaj | UI Development | 3- Completed | 2.5 | Day 7: 2.5
US-006 | T-006-04 | Test document viewing flow | 2026-09-01 | 2026-09-01 | Pankaj | Integration Test | 3- Completed | 1 | bar: Day 7
US-007 | T-007-01 | Implement analysis pipeline state | 2026-09-02 | 2026-09-02 | Pankaj | Coding | 3- Completed | 1 | bar: Day 8
US-007 | T-007-02 | Implement Docling document processing | 2026-09-02 | 2026-09-02 | Pankaj | Coding | 3- Completed | 2 | Day 8: 2
US-007 | T-007-03 | Implement document chunking | 2026-09-02 | 2026-09-02 | Pankaj | Coding | 3- Completed | 1 | bar: Day 8
US-007 | T-007-04 | Generate embeddings for document chunks | 2026-09-02 | 2026-09-02 | Pankaj | Coding | 3- Completed | 1.5 | Day 8: 1.5
US-007 | T-007-05 | Store document vectors in Qdrant | 2026-09-02 | 2026-09-02 | Pankaj | Coding | 3- Completed | 1.5 | Day 8: 1.5
US-007 | T-007-06 | Implement LangGraph analysis pipeline | 2026-09-03 | 2026-09-03 | Pankaj | Coding | 3- Completed | 3 | Day 9: 3
US-007 | T-007-07 | Integrate analysis trigger, status handling and tests | 2026-09-03 | 2026-09-03 | Pankaj | Integration Test | 3- Completed | 2 | Day 9: 2
US-008 | T-008-01 | Implement project health analysis agent | 2026-09-04 | 2026-09-04 | Pankaj | Coding | 3- Completed | 2.5 | Day 10: 2.5
US-008 | T-008-02 | Implement health score calculation | 2026-09-04 | 2026-09-04 | Pankaj | Coding | 3- Completed | 1.5 | Day 10: 1.5
US-008 | T-008-03 | Implement health score UI | 2026-09-04 | 2026-09-04 | Pankaj | UI Development | 3- Completed | 1.5 | Day 10: 1.5
US-008 | T-008-04 | Test health score calculation and display | 2026-09-04 | 2026-09-04 | Pankaj | Unit Test | 3- Completed | 1 | bar: Day 10
US-009 | T-009-01 | Implement analysis report structure | 2026-09-05 | 2026-09-05 | Pankaj | Coding | 3- Completed | 1.5 | Day 11: 1.5
US-009 | T-009-02 | Persist analysis report in MongoDB | 2026-09-05 | 2026-09-05 | Pankaj | Coding | 3- Completed | 1.5 | Day 11: 1.5
US-009 | T-009-03 | Implement analysis report UI | 2026-09-05 | 2026-09-05 | Pankaj | UI Development | 3- Completed | 2 | Day 11: 2
US-009 | T-009-04 | Test analysis report generation | 2026-09-05 | 2026-09-05 | Pankaj | Unit Test | 3- Completed | 1 | bar: Day 11
US-010 | T-010-01 | Implement project risk analysis | 2026-09-06 | 2026-09-06 | Pankaj | Coding | 3- Completed | 2 | Day 12: 2
US-010 | T-010-02 | Implement risk registry structure | 2026-09-06 | 2026-09-06 | Pankaj | Coding | 3- Completed | 1.5 | Day 12: 1.5
US-010 | T-010-03 | Implement risk list UI | 2026-09-06 | 2026-09-06 | Pankaj | UI Development | 3- Completed | 1.5 | Day 12: 1.5
US-010 | T-010-04 | Test risk analysis and registry | 2026-09-06 | 2026-09-06 | Pankaj | Unit Test | 3- Completed | 1 | bar: Day 12
US-011 | T-011-01 | Implement missing-document detection | 2026-09-06 | 2026-09-06 | Pankaj | Coding | 3- Completed | 2 | Day 12: 2
US-011 | T-011-02 | Implement missing-document result schema | 2026-09-06 | 2026-09-06 | Pankaj | Coding | 3- Completed | 1 | bar: Day 12
US-011 | T-011-03 | Implement missing-document UI | 2026-09-06 | 2026-09-06 | Pankaj | UI Development | 3- Completed | 1.5 | Day 12: 1.5
US-011 | T-011-04 | Test missing-document detection | 2026-09-06 | 2026-09-06 | Pankaj | Unit Test | 3- Completed | 1 | bar: Day 12
US-012 | T-012-01 | Implement generated-document workflow | 2026-09-07 | 2026-09-07 | Pankaj | Coding | 3- Completed | 2 | Day 13: 2
US-012 | T-012-02 | Generate executive summary, user story, risk registry and sprint plan documents | 2026-09-07 | 2026-09-07 | Pankaj | Coding | 3- Completed | 3 | Day 13: 3
US-012 | T-012-03 | Implement generated-document export | 2026-09-07 | 2026-09-07 | Pankaj | Coding | 3- Completed | 1.5 | Day 13: 1.5
US-012 | T-012-04 | Validate generated-document output | 2026-09-07 | 2026-09-07 | Pankaj | Unit Test | 3- Completed | 1 | bar: Day 13
US-014 | T-014-01 | Implement project RAG chat API | 2026-09-08 | 2026-09-08 | Pankaj | Coding | 3- Completed | 2 | Day 14: 2
US-014 | T-014-02 | Persist chat sessions | 2026-09-08 | 2026-09-08 | Pankaj | Coding | 3- Completed | 1.5 | Day 14: 1.5
US-014 | T-014-03 | Implement AI assistant chat UI | 2026-09-08 | 2026-09-08 | Pankaj | UI Development | 3- Completed | 2.5 | Day 14: 2.5
US-014 | T-014-04 | Implement grounded project-context retrieval | 2026-09-08 | 2026-09-08 | Pankaj | Coding | 3- Completed | 1.5 | Day 14: 1.5
US-014 | T-014-05 | Test AI assistant chat flow | 2026-09-08 | 2026-09-08 | Pankaj | Integration Test | 3- Completed | 1 | bar: Day 14
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 1 | Initial project flow and responsibilities were not fully defined. | Discussed the overall application flow, major modules, and responsibilities before starting implementation.
Sprint 1 | 2 | UI theme direction was not finalized. | Discussed the UI with Ma'am and agreed on a corporate-style visual direction using a light background, blue-based colors, and support for dark and dim themes.
Sprint 1 | 3 | The approach for organizing documents and analysis was still undecided. | Discussed whether users should directly upload documents or first create a project; agreed to organize documents and analysis around individual projects.
Sprint 1 | 5 | Project creation and document upload flow created an unnecessary bottleneck. | Reviewed the flow and decided to separate document upload from project creation so documents can be uploaded after the project is created.
Sprint 1 | 7 | Document processing and analysis flow needed clearer sequencing. | Discussed and finalized the sequence from document upload to processing, analysis, reports, and generated outputs.
Sprint 1 | 9 | UI theme implementation required refinement across components. | Reviewed theme behavior and updated the UI theme implementation for consistent light, dark, and dim modes.
Sprint 1 | 11 | Document handling required more reliable storage and environment setup. | Reviewed object-storage requirements and prepared the local MinIO/S3-based storage configuration.
Sprint 1 | 13 | Analysis progress was not visible enough during execution. | Discussed displaying agent processing status in the UI and implemented status updates for the analysis agents.
Sprint 1 | 14 | Final integration and stability issues remained. | Reviewed the implemented flow, fixed remaining issues, and completed backend testing and final integration checks.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-08-26 | 2026-09-08 | Pankaj | Plan the complete user flow before implementation | Making major flow decisions during implementation | Breaking features into project-based modules | Defined the project document analysis flow before further UI development.
2 | Sprint 1 | 2026-08-26 | 2026-09-08 | Pankaj | Perform testing alongside development | Waiting until the end to validate functionality | Backend validation and unit testing | Added backend test cases covering authentication, file validation, models, schemas, and analysis components.
3 | Sprint 1 | 2026-08-26 | 2026-09-08 | Pankaj | Finalize UI design direction earlier | Frequent UI changes after implementation | Using reusable UI components | Refined the UI theme and introduced additional theme styling.
4 | Sprint 1 | 2026-08-26 | 2026-09-08 | Umang | Discuss UI requirements before implementation | Implementing UI changes without confirming the intended flow | Collaborating on frontend improvements | Discussed the corporate-style UI direction and refined the theme implementation.
5 | Sprint 1 | 2026-08-26 | 2026-09-08 | Pankaj | Separate project creation from document upload | Combining project creation and document upload in one step | Organizing documents around projects | Removed document upload from project creation to avoid a bottleneck in the user flow.
6 | Sprint 1 | 2026-08-26 | 2026-09-08 | Pankaj | Maintain clearer development/setup documentation | Relying on manual environment setup | Documenting project configuration | Added an automated setup script and updated the README with setup instructions.
7 | Sprint 1 | 2026-08-26 | 2026-09-08 | Team | Review integration issues before merging | Leaving integration/configuration issues until later | Reviewing and testing changes before merging | Continued reviewing UI, backend, Docker, storage, and testing changes before integration.