## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a developer, I want a mono-repo scaffold with a FastAPI backend, a React + Vite frontend and Docker Compose services so that the whole stack runs locally with one command. | Must Have | - | Pankaj Kumar | Completed
Sprint 1 | Sprint 1 | US-02 | As a project manager, I want to create a project workspace so that every document, analysis run and report is grouped under one project. | Must Have | US-01 | Pankaj Kumar | Completed
Sprint 1 | Sprint 1 | US-03 | As a user, I want to upload .pdf, .docx, .xlsx and .csv documents with MIME, extension and size validation so that only supported files enter the pipeline. | Must Have | US-02 | Pankaj Kumar | Completed
Sprint 1 | Sprint 1 | US-04 | As a user, I want uploaded documents parsed with Docling and split into chunks so that tables and key-value content survive extraction and stay retrievable. | Must Have | US-03 | Pankaj Kumar | Completed
Sprint 1 | Sprint 1 | US-05 | As a user, I want document chunks embedded into Qdrant so that analysis output and chat answers are grounded in my own documents. | Must Have | US-04 | Pankaj Kumar | Completed
Sprint 1 | Sprint 1 | US-06 | As a project manager, I want a LangGraph pipeline that orchestrates the scope, risk, health and document-generator agents in a single run so that all insights are produced in one pass. | Must Have | US-05 | Pankaj Kumar | Completed
Sprint 1 | Sprint 1 | US-07 | As a project manager, I want risks identified with category, severity, probability, impact and the supporting evidence quote so that every finding can be traced to the source document. | Must Have | US-06 | Pankaj Kumar | Completed
Sprint 1 | Sprint 1 | US-08 | As a project manager, I want a project health score with supporting metrics so that overall delivery status is visible at a glance. | Should Have | US-06 | Pankaj Kumar | Completed
Sprint 1 | Sprint 1 | US-09 | As a user, I want dark and light theme support applied consistently across the layout so that the interface is comfortable in any environment. | Could Have | US-01 | Umang Singh | Completed
Sprint 1 | Sprint 1 | US-10 | As a user, I want drag-and-drop document upload so that adding several files is faster than using the file picker one at a time. | Should Have | US-03 | Umang Singh | Completed
Sprint 1 | Sprint 1 | US-11 | As a project manager, I want the system to recognise a risk it has already reported to me, so that each risk keeps one entry with its own status, owner, due date and full history, instead of reappearing as a brand new item every time an analysis is run. | Must Have | US-07 | Avinash Yadav | Completed; merged in PR #20 and rolled back by owner in PR #21
Sprint 1 | Sprint 1 | US-12 | As a new contributor, I want written documentation of each feature, covering how documents are read, searched and analysed and what every configuration value does, so that I can set the platform up and extend it without direct hand-holding. | Must Have | US-01 | Avinash Yadav | Completed
Sprint 2 | Sprint 2 | US-13 | As a user, I want JWT-based sign-up and sign-in so that my projects and documents are private to my own account. | Must Have | US-02 | Pankaj Kumar | Completed
Sprint 2 | Sprint 2 | US-14 | As an administrator, I want documents held in S3-compatible object storage (MinIO for local runs) so that uploaded files are not stored on the API host. | Should Have | US-03 | Pankaj Kumar | Completed
Sprint 2 | Sprint 2 | US-15 | As a user, I want live per-agent status while an analysis run is in progress so that a long-running analysis does not look frozen. | Should Have | US-06 | Pankaj Kumar | Completed
Sprint 2 | Sprint 2 | US-16 | As a developer, I want an automated pytest suite covering file validation, schemas, security helpers, models and pipeline state so that regressions are caught before a merge. | Should Have | US-06 | Pankaj Kumar | Completed
Sprint 2 | Sprint 2 | US-17 | As a developer, I want a single setup script that verifies Node, npm and Python, then provisions both environments and installs dependencies, so that onboarding takes minutes. | Could Have | US-12 | Pankaj Kumar | Completed
Sprint 1 | Sprint 2 | US-18 | As a user, I want the UI migrated to shadcn/ui with a refreshed chat surface and a simplified project-creation flow so that the interface is consistent and no step blocks project creation. | Could Have | US-09 | Pankaj Kumar / Umang Singh | Completed
Sprint 2 | Sprint 3 | US-19 | As a project manager, I want the risk register re-applied on top of the new sign-in and file-storage changes, with each user seeing only their own risks, so that risk tracking is available on the main branch. | Must Have | US-11, US-13 | Avinash Yadav | In Progress
Source: git history of https://github.com/pankajuday/AI-Project-Risk-Forecasting-Platform (94 commits, PR #1-#47, 26-Aug-2026 to 21-Sep-2026). Sprint 1 = 26-Aug-2026 to 07-Sep-2026, Sprint 2 = 08-Sep-2026 to 21-Sep-2026. Assignee names are the commit / PR authors on the repository.
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 245 | 220 | 209 | 209 | 204 | 187.5 | 153.5 | 110 | 98 | 72 | 62.5 | 46.5 | 32 | 21 | 7
SPRINT 1 BACKLOG
US-01 | T-01 | Initialise mono-repo: FastAPI application skeleton, React + Vite frontend, editorconfig and base configuration. | 2026-08-26 | 2026-08-27 | Pankaj Kumar | Design / Coding | Completed | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-02 | Author docker-compose services for MongoDB and Qdrant; correct volume names and expose the frontend port. | 2026-08-30 | 2026-08-30 | Pankaj Kumar | Coding | Completed | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T-03 | Write backend and frontend Dockerfiles; raise pip timeout and retries so the image build survives slow package mirrors. | 2026-08-31 | 2026-08-31 | Pankaj Kumar | Coding | Completed | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-04 | Model Project in Beanie and expose create / list / detail / delete project routes. | 2026-08-29 | 2026-08-30 | Pankaj Kumar | Coding | Completed | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-05 | Build the document upload endpoint with the file validator (extension, MIME sniffing, max upload size). | 2026-08-31 | 2026-09-01 | Pankaj Kumar | Coding | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-06 | Integrate the Docling document loader and the chunking strategy for PDF, DOCX, XLSX and CSV input. | 2026-09-01 | 2026-09-03 | Pankaj Kumar | Coding | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 6.5 | 3.5 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-07 | Wire the Gemini embedding model and the Qdrant collection; implement the retriever used by the agents and chat. | 2026-09-03 | 2026-09-05 | Pankaj Kumar | Coding | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5.5 | 2.5 | 0 | 0 | 0 | 0
US-06 | T-08 | Implement the LangGraph orchestrator and the shared pipeline state passed between agent nodes. | 2026-09-04 | 2026-09-06 | Pankaj Kumar | Coding | Completed | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 4 | 0 | 0 | 0
US-07 | T-09 | Write the risk agent prompt and the structured-output schema (category, severity, probability, impact, evidence). | 2026-09-05 | 2026-09-06 | Pankaj Kumar | Coding | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0
US-08 | T-10 | Implement the health agent and the project health score; remove emoji from generated output so reports render cleanly. | 2026-08-30 | 2026-09-02 | Pankaj Kumar | Coding | Completed | 6 | 6 | 6 | 6 | 6 | 4.5 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-11 | Add the dark / light theme toggle and fix light-mode styling across the layout and shared components. | 2026-08-30 | 2026-08-31 | Umang Singh | Coding | Completed | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-12 | Build the drag-and-drop upload zone on the documents tab with progress and rejection feedback. | 2026-08-31 | 2026-09-01 | Umang Singh | Coding | Completed | 5 | 5 | 5 | 5 | 5 | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-13 | Design the rule that decides whether a risk found in a new analysis run is one already in the register: first compare the exact sentence quoted from the document as evidence, then compare a short signature built from the risk's category and the important words of its title, and finally compare how many important words the two risks share (a match needs at least 25 per cent overlap). | 2026-08-29 | 2026-08-30 | Avinash Yadav | Design | Completed | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-14 | Build the matching module (risk_identity.py): reduce a risk's text to its important words, build the signature, score the word overlap between two risks, and sort each newly reported risk into matched, new or no-longer-reported. The module makes no database or network calls, so it can be tested on any machine. | 2026-08-30 | 2026-08-31 | Avinash Yadav | Coding | Completed | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-15 | Create the two database records: one row per unique risk in a project (status, owner, due date, first and last seen dates, number of times reported and highest severity reached) and one row for every change made to it. Define the five statuses (open, mitigating, resolved, accepted and stale) and which changes between them are allowed. | 2026-08-31 | 2026-08-31 | Avinash Yadav | Coding | Completed | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-16 | Build the layer that writes the matching result to the database (risk_reconciler.py): add risks reported for the first time, refresh the wording of risks already known, re-open a closed risk that has been reported again, record a rise or fall in severity, and mark risks the latest run no longer reports as stale. | 2026-08-31 | 2026-09-01 | Avinash Yadav | Coding | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-17 | Build the risk API: list a project's risks with filters for status, category, owner, severity and overdue items; return summary counts; return one risk with its full change history; update status, owner, due date or closing note; and add a note. | 2026-09-01 | 2026-09-01 | Avinash Yadav | Coding | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-18 | Add the background check that flags risks whose due date has passed, recording one overdue entry per risk per day so the history is not flooded. | 2026-09-01 | 2026-09-01 | Avinash Yadav | Coding | Completed | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-19 | Connect the matching step to the end of the analysis pipeline and register the new records and API routes when the application starts, ensuring that a failure in this step can never fail the analysis itself. | 2026-09-01 | 2026-09-01 | Avinash Yadav | Coding | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-20 | Write 19 automated tests for the matching logic: the signature is the same for one risk however its title is worded, two categories stay separate, reworded risks still match, unrelated risks do not, and every reported risk ends up in exactly one group. | 2026-09-01 | 2026-09-01 | Avinash Yadav | Testing | Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-21 | Build the Risk Register screen: summary cards, filters for status, category and overdue items, the risk table, a detail panel showing the change history, and controls to set owner, due date and status or add a note. | 2026-08-31 | 2026-09-01 | Avinash Yadav | Coding | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-22 | Add the frontend API calls and shared type definitions used by the Risk Register screen. | 2026-09-01 | 2026-09-01 | Avinash Yadav | Coding | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-23 | Raise PR #20, respond to review feedback and merge; the change was subsequently rolled back by the repository owner in PR #21. | 2026-09-01 | 2026-09-01 | Avinash Yadav | Review | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-24 | Rewrite the README feature and architecture sections so they describe what the platform actually does: how documents are read, how every answer is tied back to the source documents, which analysis agents run, and how risks are tracked over time. | 2026-09-01 | 2026-09-01 | Avinash Yadav | Documentation | Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-25 | Write the feature-by-feature technical documentation: upload, document reading, splitting into sections, indexing for search, retrieval, the analysis agents and report generation. | 2026-09-02 | 2026-09-04 | Avinash Yadav | Documentation | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5.5 | 2.5 | 0 | 0 | 0 | 0 | 0
US-12 | T-26 | Document the risk register for the rest of the team: what is stored for each risk, which status changes are allowed, the kinds of history entries, and what each API endpoint accepts and returns. | 2026-09-02 | 2026-09-03 | Avinash Yadav | Documentation | Completed | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-27 | Check the backend, frontend and Docker configuration tables and the setup steps against a fresh copy of the project, and correct what was missing or wrong. | 2026-09-05 | 2026-09-06 | Avinash Yadav | Documentation | Completed | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 0 | 0 | 0
US-06 | T-28 | Fix the empty-document workspace analysis path and surface the error state in the UI. | 2026-08-31 | 2026-08-31 | Pankaj Kumar | Bug Fix | Completed | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-29 | Begin the shadcn/ui migration: add the component primitives, convert the chat surface and normalise the dark and light palettes. | 2026-09-05 | 2026-09-06 | Pankaj Kumar / Umang Singh | Coding | Completed | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0
US-18 | T-30 | Redesign the create-project page. | 2026-09-07 | 2026-09-07 | Pankaj Kumar | Coding | Completed | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0
SPRINT 2 BACKLOG
US-13 | T-31 | Implement the JWT authentication backend: register and login routes, password hashing, token issue and the auth dependency guarding project routes. | 2026-09-08 | 2026-09-08 | Pankaj Kumar | Coding | Completed | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-32 | Add the authentication screens, token storage and protected routing to the frontend, with related UI maintenance. | 2026-09-08 | 2026-09-08 | Pankaj Kumar | Coding | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T-33 | Add boto3, the S3 client wrapper and the document storage abstraction; move the upload and fetch paths onto object storage. | 2026-09-08 | 2026-09-09 | Pankaj Kumar | Coding | Completed | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T-34 | Add the MinIO service to docker-compose and document the root credentials used for local runs. | 2026-09-09 | 2026-09-09 | Pankaj Kumar | Coding | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-35 | Complete the shadcn/ui migration across the remaining pages and add the blue-sky theme. | 2026-09-15 | 2026-09-16 | Pankaj Kumar / Umang Singh | Coding | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-36 | Remove the inline document-upload step from project creation and move it to the documents tab. | 2026-09-16 | 2026-09-16 | Pankaj Kumar | Coding | Completed | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-37 | Publish per-agent pool status from the backend and render each agent's live state during an analysis run. | 2026-09-16 | 2026-09-16 | Pankaj Kumar | Coding | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-38 | Fix the project total-chunk count that was not being aggregated after ingestion. | 2026-09-16 | 2026-09-16 | Pankaj Kumar | Bug Fix | Completed | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T-39 | Write the backend pytest suite covering the file validator, schemas, security helpers, models, pipeline state and document-controller utilities, using binary file headers instead of fixture files. | 2026-09-20 | 2026-09-21 | Pankaj Kumar | Testing | Completed | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 0
US-17 | T-40 | Write the project setup script: verify Node, npm and Python, provision both environments and install all dependencies. | 2026-09-21 | 2026-09-21 | Pankaj Kumar | Coding | Completed | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0
US-01 | T-41 | Rename the Docker Compose project and containers to match the platform name and refresh the README setup section. | 2026-09-21 | 2026-09-21 | Pankaj Kumar | Coding | Completed | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0
US-19 | T-42 | Rebase the risk-register branch onto the authentication and object-storage refactor and resolve the conflicts in application startup, the orchestrator and the project detail page. | 2026-09-19 | 2026-09-21 | Avinash Yadav | Coding | In Progress | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 4 | 3
US-19 | T-43 | Add per-user scoping and authorisation checks to the /risks endpoints before the pull request is re-raised. | 2026-09-21 | 2026-09-21 | Avinash Yadav | Coding | Not Started | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
Day 1-Day 14 hold the remaining effort in hours at the end of each sprint day (burn-down input); row 3 totals them. Sprint 1 Day 1 = 26-Aug-2026 (13 days, so Day 14 is 0) and Sprint 2 Day 1 = 08-Sep-2026 (14 days). Effort figures are the team's estimates recorded at sprint planning; task rows are derived from the repository commits and pull requests listed in the Product Backlog note. Terms: "signature" is a short code built from a risk's category and the important words of its title, used to recognise the same risk in a later analysis run (called a fingerprint in the code); "word overlap" is a 0-to-1 score of how many important words two risks share.
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 5 | docker-compose used mismatched volume names and the frontend port was not published, so the UI was unreachable from the host. | Volume names corrected and port 5173 exposed (PR #3); verified with docker compose ps by all three members.
Sprint 1 | Day 5 | The health agent emitted emoji into generated report text, which broke rendering in the report view. | Emoji stripped from the health agent output template (PR #4).
Sprint 1 | Day 6 | pip install -r requirements.txt failed on Linux and inside the backend image because pywin32 is Windows-only. | Platform marker added so pywin32 is skipped on non-Windows hosts (PR #11); requirements restored from the initial PR (PR #7).
Sprint 1 | Day 6 | The backend image build kept timing out while downloading packages. | pip timeout and retry count raised in the backend Dockerfile (PR #10).
Sprint 1 | Day 6 | The frontend build broke after a refactor: theme_provider was imported from the wrong path. | Import path corrected in src/main (PR #14); light-mode CSS and logo fixed alongside (PR #15).
Sprint 1 | Day 6 | Uvicorn ignored the host and port from .env, so the API started on the wrong port. | Environment configuration read correctly at startup (PR #13).
Sprint 1 | Day 6 | An analysis triggered on a project with no documents crashed the run instead of reporting an empty workspace. | Guard added in the analysis path and the empty state surfaced in the UI (PR #17).
Sprint 1 | Day 7 | The risk matching logic could not be tested without a running MongoDB, which would have left the test suite unusable on other machines. | Matching logic kept free of database and network calls and covered by 19 automated tests that run anywhere; only a thin layer around it touches the database.
Sprint 1 | Day 7 | The risk register change touched application startup, the end of the analysis pipeline and the project detail page, all of which were being reworked at the same time. | PR #20 was merged and then rolled back by the repository owner in PR #21; re-applying the change was moved to the Sprint 2 backlog as US-19.
Sprint 2 | Day 1 | Authentication landed on the backend while the UI still called the API anonymously. | Auth screens, token handling and protected routes added to the frontend (PR #37).
Sprint 2 | Day 2 | Documents were written to the API host filesystem, which blocked running more than one backend instance. | S3-compatible storage introduced with MinIO for local runs (PR #38, PR #39).
Sprint 2 | Day 9 | The project overview reported a wrong total chunk count after ingestion. | Chunk aggregation fixed in the pipeline (PR #43).
Sprint 2 | Day 9 | Long analysis runs gave no feedback, so users assumed the application had hung. | Per-agent pool status published to the UI while the pipeline runs (PR #41).
Sprint 2 | Day 9 | The document-upload field inside the create-project form blocked project creation when a file failed validation. | Upload step removed from project creation and moved to the documents tab (PR #40).
Sprint 2 | Day 14 | New contributors were spending hours on environment setup before running the stack. | Setup script added to check tooling and install dependencies, with README instructions (PR #45, PR #46).
Sprint 2 | Day 14 | Re-applying the risk register is blocked until it is agreed how each user is restricted to their own risks. | Approach agreed with the repository owner; tasks T-42 and T-43 carried into the next sprint under US-19.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-08-26 | 2026-09-07 | Pankaj Kumar | Freeze the files that application startup and the analysis pipeline touch while a large feature branch is open. | Merging a wide-reaching pull request on the same day it is raised, without a rebase against main. | One small pull request per concern; 47 focused PRs kept review fast and every revert cheap. | Rebase window agreed before a merge; US-19 raised to re-integrate the risk register in a quiet part of the codebase.
2 | Sprint 1 | 2026-08-26 | 2026-09-07 | Avinash Yadav | Splitting a feature into plain logic and a thin database layer from the first commit, which made the 19 automated tests possible without a database. | Building backend, API and UI for one feature in a single pull request; the 14-file change was hard to review and harder to roll back. | Writing the documentation with the feature rather than after it, so the README and the code described the same system. | The next slice of the register will ship as three pull requests (matching logic, endpoints, then screen), with the branch brought up to date daily.
3 | Sprint 1 | 2026-08-26 | 2026-09-07 | Umang Singh | Checking light and dark palettes on every component touched, not just the page being changed. | Assuming theme fixes are local; a provider import path broke the whole build. | Small UI pull requests reviewed the same day. | Theme and layout checks added to the review checklist in CONTRIBUTING.md.
4 | Sprint 2 | 2026-09-08 | 2026-09-21 | Pankaj Kumar | Automating environment setup earlier; the setup script removed the most common onboarding question. | Deferring the backend test suite to the end of the sprint, which left two fix commits untested until the final days. | Keeping authentication, storage and UI work on separate branches with descriptive commit prefixes. | Test suite runs before every merge from the next sprint; setup script documented in the README.
5 | Sprint 2 | 2026-09-08 | 2026-09-21 | Avinash Yadav | Documenting configuration values against a fresh copy of the project instead of a working machine, which surfaced three undocumented values immediately. | Waiting for a refactor to settle before rebasing; the gap grew to three weeks of main-branch changes. | Writing down the status rules and the behaviour of each endpoint, which made the rebase in T-42 manageable. | Risk-register branch brought up to date with main, and per-user access rules written down before the pull request is raised again.
6 | Sprint 2 | 2026-09-08 | 2026-09-21 | Umang Singh | Reusing shadcn primitives instead of hand-rolling components for each page. | Duplicating upload logic between the create-project form and the documents tab. | Pairing on UI review so design feedback arrives before the pull request. | Upload flow consolidated on the documents tab (PR #40).