## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Pankaj Kumar | 2026-08-30 | docker-compose used mismatched volume names for the MongoDB and Qdrant services and the frontend port was not published, so the UI could not be reached from the host. | Sprint 1 | Pankaj Kumar | Maintainability | Volume names corrected and the frontend port exposed in docker-compose (PR #3). | 2026-08-30 | Closed | Verified by all three members with docker compose ps and a browser check.
2 | Umang Singh | 2026-08-30 | The health agent emitted emoji into generated report text, which broke rendering of the report view and the exported document. | Sprint 1 | Pankaj Kumar | Standards | Emoji removed from the health agent output template (PR #4). | 2026-08-30 | Closed | Plain-text-only rule added for agent output.
3 | Avinash Yadav | 2026-08-30 | requirements.txt had drifted from the initial pull request and was missing packages, so the backend failed to start on a clean environment. | Sprint 1 | Pankaj Kumar | Maintainability | requirements.txt restored from the initial pull request (PR #7). | 2026-08-30 | Closed | Found while setting up a fresh clone for the risk register work.
4 | Avinash Yadav | 2026-08-31 | pip install -r requirements.txt failed on Linux hosts and inside the backend image because pywin32 is a Windows-only dependency. | Sprint 1 | Pankaj Kumar | Maintainability | Platform marker added so pywin32 is skipped on non-Windows platforms (PR #11). | 2026-08-31 | Closed | Blocked both the Docker build and the Linux dev setup.
5 | Pankaj Kumar | 2026-08-31 | The backend Docker image build timed out while downloading Python packages on slower connections. | Sprint 1 | Pankaj Kumar | Maintainability | pip timeout and retry count raised in the backend Dockerfile (PR #10). | 2026-08-31 | Closed | Build time now stable on the team's machines.
6 | Umang Singh | 2026-08-31 | The frontend build failed after a refactor because theme_provider was imported from the wrong path in src/main. | Sprint 1 | Pankaj Kumar | Logical | Import path corrected (PR #14). | 2026-08-31 | Closed | Caught immediately after the theme toggle merge.
7 | Umang Singh | 2026-08-31 | The application logo did not render and light-mode CSS was broken across the layout and shared components. | Sprint 1 | Pankaj Kumar | User Interface | Logo asset path and light-mode styles fixed (PR #15). | 2026-08-31 | Closed | Theme check added to the UI review checklist.
8 | Pankaj Kumar | 2026-08-31 | Uvicorn ignored BACKEND_HOST and BACKEND_PORT from the .env file, so the API bound to a different port than the frontend expected. | Sprint 1 | Pankaj Kumar | Logical | Environment configuration read correctly during application startup (PR #13). | 2026-08-31 | Closed | API now consistently served on 127.0.0.1:3000.
9 | Avinash Yadav | 2026-08-31 | Triggering an analysis on a project that had no indexed documents crashed the run instead of reporting an empty workspace. | Sprint 1 | Pankaj Kumar | Logical | Guard added on the analysis path and the empty-workspace state surfaced in the UI (PR #17). | 2026-08-31 | Closed | Found while running the analysis pipeline to produce test data for the risk register.
10 | Pankaj Kumar | 2026-09-07 | The document loader resolved the uploads folder relative to the current working directory, so ingestion failed when the API was started from the repository root. | Sprint 1 | Pankaj Kumar | Logical | Upload folder path resolution fixed in the document loader (PR #29). | 2026-09-07 | Closed | Path now derived from the application base directory.
11 | Pankaj Kumar | 2026-09-01 | The risk register change (PR #20) altered application startup, the end of the analysis pipeline and the project detail page, which were the same areas being reworked at the same time for sign-in and file storage, and the merge left the main branch in a conflicting state. | Sprint 1 | Avinash Yadav | Maintainability | The merge was rolled back by the repository owner in PR #21. Re-applying it is tracked as US-19: bring the branch up to date with the sign-in and file-storage changes (T-42), then restrict each user to their own risks (T-43). | 2026-09-01 | Open | Still in progress at the end of Sprint 2; the pull request will be raised again once the per-user access rules are agreed. The feature code, its API and its 19 automated tests are unchanged.
12 | Avinash Yadav | 2026-09-16 | The project overview reported an incorrect total chunk count after document ingestion. | Sprint 2 | Pankaj Kumar | Logical | Chunk aggregation corrected in the ingestion pipeline (PR #43). | 2026-09-16 | Closed | The count now matches the number of document sections actually indexed.
13 | Umang Singh | 2026-09-16 | A long analysis run gave no progress feedback, so users could not tell whether the pipeline was still working. | Sprint 2 | Pankaj Kumar | User Interface | Per-agent pool status published from the backend and rendered live in the UI (PR #41). | 2026-09-16 | Closed | Each agent's state is now visible while the pipeline runs.
14 | Avinash Yadav | 2026-09-16 | The inline document-upload field inside the create-project form blocked project creation whenever a file failed validation. | Sprint 2 | Pankaj Kumar | User Interface | Upload step removed from project creation and moved to the documents tab (PR #40). | 2026-09-16 | Closed | Project creation is now a single-step form.
Source: fix commits and pull requests in https://github.com/pankajuday/AI-Project-Risk-Forecasting-Platform (Sprint 1 = 26-Aug-2026 to 07-Sep-2026, Sprint 2 = 08-Sep-2026 to 21-Sep-2026). Type Of Defect uses the values defined on Sheet2. Serial 11 is the only item still open at the end of Sprint 2.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others