## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Pankaj | 2026-08-30 | Theme toggle and light-mode styling were inconsistent across the UI. | Sprint 1 | Umang | User Interface | Fixed theme toggle behavior and aligned light-mode styling across components. | 2026-08-30 | Closed | Theme toggle and light-mode styling were rechecked across the updated UI for consistent behavior.
2 | Pankaj | 2026-08-30 | Docker volume names and the frontend port were not configured correctly. | Sprint 1 | Pankaj | Logical | Corrected volume names and exposed the frontend port. | 2026-08-30 | Closed | Docker volumes and the frontend port were rechecked after the configuration update.
3 | Pankaj | 2026-08-31 | Docker dependency installation failed because pywin32 is not needed on Linux. | Sprint 1 | Pankaj | Maintainability | Excluded pywin32 on Linux-based environments. | 2026-08-31 | Closed | Linux dependency setup was rechecked to ensure pywin32 is skipped where it is not required.
4 | Pankaj | 2026-08-31 | Backend Docker builds could fail while installing dependencies due to short timeouts. | Sprint 1 | Pankaj | Maintainability | Added longer install timeouts and retry handling. | 2026-08-31 | Closed | The backend image build was rechecked after adding retries and a longer dependency-install timeout.
5 | Pankaj | 2026-08-31 | Docker Compose used incorrect paths and environment configuration. | Sprint 1 | Pankaj | Logical | Corrected Compose paths and environment settings. | 2026-08-31 | Closed | Docker Compose was rechecked to confirm the updated paths and environment settings load correctly.
6 | Pankaj | 2026-08-31 | Empty documents caused problems during project analysis. | Sprint 1 | Pankaj | Logical | Handled empty-document analysis and updated the frontend flow. | 2026-08-31 | Closed | An empty document was checked through the analysis flow and is now handled without breaking the workspace.
7 | Pankaj | 2026-09-04 | Frontend error states were not presented clearly during document operations. | Sprint 1 | Pankaj | User Interface | Improved error handling and error feedback in the document UI. | 2026-09-04 | Closed | Document upload errors were rechecked to confirm clearer feedback is shown in the UI.
8 | Pankaj | 2026-09-07 | The document loader used an incorrect path for the uploads folder. | Sprint 1 | Pankaj | Logical | Fixed the upload-folder path used by the document loader. | 2026-09-07 | Closed | Document processing was rechecked after correcting the uploads-folder path.
9 | Pankaj | 2026-09-16 | The project's total chunk count was not being calculated. | Sprint 1 | Pankaj | Logical | Fixed the pipeline calculation for total project chunks. | 2026-09-16 | Closed | Project chunk totals were rechecked after fixing the pipeline calculation.
10 | Pankaj | 2026-09-16 | Document upload during project creation created a workflow bottleneck. | Sprint 1 | Pankaj | User Interface | Removed document upload from project creation and kept it as a separate step. | 2026-09-16 | Closed | Project creation was rechecked without file upload so document upload can be handled as a separate step.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others